## Sheet1
Risk Matrices	Column1	Column2	Column3	Column4	Column5
	Neglible	Minor	Major	Hazardous	Catastrophic			Risk	Statement	Response	Objective	Likelihood	Impact	Risk Level
Very unlikely	Low	low	Low meduim	medium	Meduim			Computer Breaking	My computer hardware or software could have an issue that prevents me from completing the task	I have 2 spare laptops and I am frequently pushing to GitHub		Very Unlikely	Minor	low
Unlikely	low	low meduim	Low meduim	medium	Meduim High			Finacial difficulty	The investors in the estate agent website may not be able to pay to complete the project	The website has been comissioned by a startup so I have taken payment in advacne		Unlikely	Major	low medium
Moderate	low	low meduim	meduim	medium High	Meduim High			Rivals infulencing website	The website will have large rivals such as RightMove and Zoopla they could pressure the website investor to change it	We have agreed on what the finished product will look like and stated what day it shoule be delivered by		Unlikely	Major	low medium
Likely	low	low meduim	meduim	meduim High	High			connection issues	I coule lose my internet connection	I have mobile data I can use to connect with stakeholders and I can use a coffee shop wifi to push changes to github		Very Unlikely	Major	low medium
Highly Likely	low meduim	meduim	meduim high	High	High			Lack of knowledge	I could encouter issues in the program that I do not have the skills to solve	I have taken a separate course on Udemy so I am better prepared		Highly Likely	Major	Meduim High
								3rd party software issues	For example postman, my testing software could have server issues.	I will have to find a new testing software for my database		Very Unlikely	minor	low
								An accident happens to me	I could have an accident in or outside the project which requires time away for treatment	As a low likelyhood event I do not need to do much excepet be vigilant.		Very Unlikely	Hazadous	Meduim
								Flooding	An area near me has previosuly flooded this caused a power outage before.	I have a backup petrol generator and enough fuel for the duration of the project		Very Unlikely	Catastrophic	Meduim